## backlog
State | ID | Work Item Type | Title | Acceptance Criteria | Description | Story Points | Parent
New | 286614 | Epic | Data Strategy Accelerator |  | Implement the data strategy accelerator package.
New | 286615 | Feature | Deploy IP Kit |  | Deploy the IP Kit in the customer environment using GitHub Actions. The variable files should be updated based on the customer requirements. |  | 286615
New | 286616 | Feature | Reuse/Add New Ingestion Patterns |  | Reuse the existing ingestion patters or create new ones. If new ingestion patterns need to be created, then they need to follow the same general pattern as the existing ones. |  | 286614
New | 286617 | Feature | Stage Data |  | Move ingested data to raw. Then move raw data to staging. Before data is staged, data quality checks need to be run. |  | 286614
New | 286618 | Feature | Curate Data |  | Move staged data to the curated layer. Data should be prepared as star schema model for Power BI and/or custom preparation is done for machine learning inputs. |  | 286614
New | 286619 | Feature | Visualize Data |  | Create data visualizations and conduct performance testing so data visualizations are as responsive as possible. |  | 286614
New | 286620 | User Story | Set up Service Principal | Verify that: 1. A service principal is created for use by the GitHub Action that deploys the Azure resources 2. The Service Principal is assigned rights in the Subscription. There's 2 Options - Assign the Service Principal RBAC Owner rights at the Subscription(s) - Pre-create all Resource Groups and Assign the Service Principal Owner RBAC Owner rights at each Resource Group 3. Create a federated credential for the service principal - If you're using environments: - Please use an entity type of environment - You will need to create a new federated credential for each environment you're deploying - The IP kit deploys up to 3 environments: **development**, **test**, and **production** | Create a service principal with permissions in the target Azure subscription. |  | 286615
New | 286621 | User Story | Set up GitHub Repo | 1. Verify that the following GitHub Secrets are created with the same name: - **TENANT_ID** - [how to find](https://learn.microsoft.com/en-us/azure/active-directory/fundamentals/active-directory-how-to-find-tenant#find-tenant-id-through-the-azure-portal) - **SUBSCRIPTION_ID** - [how to find](https://learn.microsoft.com/en-us/azure/azure-portal/get-subscription-tenant-id#find-your-azure-subscription) - **SERVICE_PRINCIPAL_CLIENT_ID** (From Step 1) - [how to find](https://learn.microsoft.com/en-us/azure/active-directory/develop/app-objects-and-service-principals#application-object) 2. Create the below secrets *with the same name* if you're creating private endpoints - **DNS_ZONE_SUBSCRIPTION_ID** | Create GitHub repo, add data strategy code, add GitHub Action secrets. |  | 286615
New | 286622 | User Story | IP Kit Post Deployment Tasks | 1. Post Deployment Tasks - Azure SQL - Execute the below stored procedure in the deployed Azure SQL Database(s) -Login with AAD. SQL Auth is disabled. - EXEC [dbo].[AddManagedIdentitiesAsUsers] 2. Post Deployment Tasks - Synapse - Execute the below stored procedure in the Synapse Serverless Database StoredProcDB - Login with AAD. SQL Auth is disabled post deployment. - EXEC [dbo].[AddManagedIdentitiesAsUsers] - If you're deploying the logic app, run the following precreated SQL script in the Synapse portal: RunForLogicApp 3. Post Deployment Tasks - Purview - Add the ADF and Synapse managed identities as Data Curator's in the Root Collection of Purview - This is required for lineage - When lake DBs are created, you will need to execute the below commands for Purview to scan - CREATE LOGIN [PurviewAccountName] FROM EXTERNAL PROVIDER; - CREATE USER [PurviewAccountName] FOR LOGIN [PurviewAccountName]; - ALTER ROLE db_datareader ADD MEMBER [PurviewAccountName]; - If your deploying all resources with no public access behind a virtual network and your service principal didn't have Owner RBAC rights on the Subscription Get Owner of Subscription to Provide AAD Group with Contributor Access to Purview Managed Resource Group if you set the feature flag, DeployPurviewIngestionPrivateEndpoints, to true Within the Azure Portal, navigate to Purview's managed Storage Account and Event Hub. For each resource, approve the pending Private Endpoint connections created by the GitHub Action. If your deploying all resources with no public access behind a virtual network Set up a Managed VNET Integration Runtime to scan supported Azure data sources Set up a Self-Hosted Integration Runtime to scan data sources unsupported by the Managed VNET Integration Runtime | Manual updates to Azure resources after deployment. |  | 286615
New | 286623 | User Story | Input Values in the Networking Setup Variable Files | For each environment: 1. Verify if the client uses private endpoints and private endpoints are enabled/disabled as appropriate 2. Verify if the client needs to deploy resources with vnet injection and, if yes, vnet injection is enabled 3. Verify that the correct values are inputted for the virtual networks, subnets, and resource groups | As a DevOps engineer, I want to specify the appropriate values in the networking variable files so that the IP Kit resources are deployed with private endpoints and VNET injection where necessary. |  | 286615
New | 286624 | User Story | Input Values in the General Variable Files | For each environment: 1. Verify that the proper azure resource location is inputted 2. Verify that the resource names are inputted for resources that will be deployed 3. Verify that the required tag values are inputted | As a DevOps engineer, I want to specify the appropriate values in the general variable files so that the IP Kit resources are deployed with the correct naming convention, tags, azure resource location, and highly important resource attributes. |  | 286615
New | 286625 | User Story | Input Values in the Feature Flag Variable Files | For each environment: 1. Verify that the feature flags for the required resource are set to true 2. Verify that the feature flags for the non-required resource are set to false 3. Verify that the required tag values are inputted | As a DevOps engineer, I want to specify the appropriate values in the feature variable files so that the IP Kit resources are deployed with only the relevant resources that the client needs for their use case. |  | 286615
New | 286626 | User Story | Input Values in the Entra Assignments Variable Files | For each environment where the Assign_RBAC_On_Deployment feature flag is set to true: 1. Verify that the group id and group name values for Entra_Group_Admin are inputted 2. Verify that the group id and group name values for Entra_Group_Shared_Service are inputted 3. If the client is using a Data Governance Entra Group, Verify that the group id and group name values for Entra_Group_Governance are inputted 4. If the client is using Data Publisher Entra Groups, verify that the group ids and storage folder path values for Entra_Groups_Data_Publishers are inputted 5. If the client is using Data Publisher Entra Groups, verify that the app ids and storage folder path values for Assign_RBAC_for_Producers are inputted 6. If the client is using Data Consumers Entra Groups, verify that the app ids are inputting for Entra_Groups_Data_Consumers are inputted 7. If the client is using a CI/CD service principal, verify that the application id is inputted for Assign_RBAC_for_CICD_Service_Principal | As a DevOps engineer, I want to specify the appropriate values in the entra assignment variable files so that the IP Kit can assign the necessary RBAC in Azure to the relevant Entra Groups and Service Principals. |  | 286615
New | 286627 | User Story | Create control table records for source to landing | For control table records with existing pattern: 1. Create control table records that align with pattern in ReadME For control table records for new ingestion patterns: 1. Each new source will have their own custom json fields within SourceObjectSettings, SourceConnectionSettingsName, and CopySourceSettings. These fields will be related to the linked service and dataset parameters required for the dataset. Please verify that these values are properly designed for the ingestion pipeline. Other fields should be align with the Oracle/M365 ingestion patterns 2. Create control table records that aligns with new ingestion patterns | As a Data engineer, I need to create control table records to move data from source to landing so that data can be moved using a metadata driven process. |  | 286615
New | 286628 | User Story | Create control table records for landing to raw | Verify that: 1. A control table record is created for full data lods 2. A control table record is created for incremental data loads The values should align with the example control table records in the README | As a Data engineer, I need to create control table records to move data from landing to raw so that data can be moved using a metadata driven process. |  | 286615
New | 286629 | User Story | Create new ingestion pattern (example) | Verify that: 1. A new highly parameterized data pipeline is created that ingests the new data source. Please reference the Azure SQL, Oracle, and M365 pipelines as an example 2. Verify that the pipline is triggered through the PL_1_Source_to_Landing_Step1 pipeline like the other ingestion pipelines | As a Data engineer, I want to create a new ingestion pattern for Netezza so that I can ingest data. |  | 286615
New | 286630 | User Story | Create control table records for raw to staging | Verify that: 1. A control table record is created that aligns with the example control table records in the README | As a Data engineer, I need to create control table records to move data from raw to staging so that data can be moved using a metadata driven process. |  | 286617
New | 286631 | User Story | Design and Implement Data Quality Checks for Ingested Data | Verify that: 1. Data quality checks are defined by the client 2. The data quality checks are implemented before data is writted to the staging zone | As a Data engineer, I want to create relevant data quality checks on data I ingested to raw so that data in staging is ready to be used for data modeling and other consumption |  | 286617
New | 286632 | User Story | Design Star Schema Model | Verify that: 1. The data model is designed with the client and the data visualization team 2. Verify the data model uses only 1:M relationship for PBI performance purposes 3. Verify the data model uses a strictly star schema model (not snowflake) for PBI performance purposes | As a Data engineer, I want to create a data model so that I can ingest data into a format suitable for Power BI and the use case requirements. |  | 286618
New | 286633 | User Story | Move Data to Curated Zone | Verify that: 1. The data in the staging zone is moved to curated in the format required for the created data model | As a Data engineer, I want to move data from staging to curated in the format that is expected for the star schema model that was designed. |  | 286618
New | 286634 | User Story | Work with Data Engineering team to define data model | Verify that: 1. The data visualization team works with the data engineering team to define the data model | As an enterprise data analyst, I need to work with the data engineers creating the data model to ensure the proper fields are available for my data visualizations. |  | 286619
New | 286635 | User Story | Create data visualizations | Verify that: 1. The required dashboards are created 2. The required filters are added to the dashboards 3. The dashboard connects to the source data using direct query | As an enterprise data analyst, I need to create visualizations that satisfy the needs of the customer use case so that the customer can obtain insights from their data |  | 286619
New | 286636 | User Story | Performance tune data visualizations | Verify that: 1. The team works with the data engineering team to update the data model to improve performance 2. The team uses the best PBI performance tuning practices | As an enterprise data analyst, I need to performance tune the data visualizations by working to ensure I'm using Power BI best practices and that the data model is in the correct format and structure so that my data visualizations are as responsive as possible. |  | 286619